## Backlog
ID | Item | Sprint | Assignee
1 | Write a concise purpose statement for the project | 1 | Troy
2 | Decide on a set of high-level entities, and describe their relationships | 1 | Everyone
3 | Create an interaction Diagram to describe the interactions of the high-level entities | 1 | Everyone
4 | Describe the interactions in that diagram with descriptions and UML | 1 | Troy, McLain, Abdul
5 | Establish the risks, benefits, and assumptions of the project | 1 | Marshall
6 | Set up framework code based on the UML diagram to allow team members to fill in implementations | 2 | Troy
7 | Splash screen appears when program begins | 2 | Troy
8 | Splash screen includes a (somewhat working) blinking "ENTER" button | 2 | Troy
9 | Splash screen displays instructions upon being entered on a new screen | 2 | Troy
10 | Next screen allows user to choose how many pancakes to stack | 2 | McLain
11 | Same screen allows user to set the difficulty of their opponent | 2 | McLain
12 | Handle incorrect difficulty input | 2 | McLain
13 | Allow user to choose an order for the pancake stacks before the game or choose a random order | 2 | Marshall
14 | Validate user order or use C++ STL to shuffle the pancakes | 2 | Marshall
15 | Allow player to enter their initials on the next screen | 2 | Abdul
16 | Allow player to see the high scores loaded from the file on that same screen | 2 | Abdul
17 | Draw one pancake | 3 | Marshall
18 | Draw a stack of pancakes in its own window | 3 | Marshall
19 | Draw another stack of pancakes in a separate window without affecting the other stack | 3 | Marshall
20 | Allow user to make a selection using arrow keys | 3 | McLain
21 | Access a data structure containing the pancake draw instructions for each pancake and print them individually | 3 | McLain
22 | Blink those pancakes above and including the selected pancake for 3 seconds | 3 | McLain
23 | Print the updated user stack to reflect changes | 3 | McLain
24 | Calculate the AI's move by performing a minimax tree depth search | 3 | Troy
25 | Blink the pancakes at and above the AI's choice for the player | 3 | Troy
26 | Execute the AI's move by flipping the pancakes above that choice and redraw the AI's stack | 3 | Troy
27 | When the game is over, calculate the user's score | 3 | Abdul
28 | Generate a new screen to show the user their score | 3 | Abdul
29 | On the same screen, display the previous scores read from the file, with all 6 scores sorted | 3 | Abdul
30 | Write the scores to the file, and ask the user if they would like to play again or quit | 3 | Abdul
31 | Make sure the user cannot mess up the first splash screen or instructions screen | 4 | Troy
32 | Handle illegal pancake selections | 4 | McLain
33 | Show the user their difficulty before leaving second screen | 4 | McLain
34 | Handle incorrect pancake stack orders | 4 | Marshall
35 | Show pancake stack order when leaving third screen | 4 | Marshall
36 | Cleanly display results on scores screen | 4 | Abdul
37 | Display only 5 results plus user's 0 score on same screen | 4 | Abdul
38 | Fix any issues that arise when users try our game | 5 | Everyone

## Burndown
Date | Time | Master | Members Present | Items Due | Items Completed | Items Due Count (running total) | Completed Count (running total) | Planned | Actual
2018-10-15 | 4:10 | Troy | Everyone | 1, 2 | 1, 2 | 2 | 2 | 36 | 36
2018-10-17 | 4:10 | Troy | Everyone | 3 | 3 | 3 | 3 | 35 | 35
2018-10-18 | 5:00 | Troy | Everyone | 4, 5 | 4, 5 | 5 | 5 | 33 | 33
2018-10-21 | 5:00 | Troy | Everyone | 6, 7, 10 | 6 | 8 | 6 | 30 | 32
2018-10-22 | 4:10 | Troy | Everyone | 8, 11, 13, 15 | 10, 11, 13, 15 | 12 | 10 | 26 | 28
2018-10-23 | 12:35 | Abdul | Everyone | 9, 12, 14, 16 | 7, 8, 9, 12, 14, 16 | 16 | 16 | 22 | 22
2018-10-29 | 4:10 | Marshall | Everyone | 18, 20, 28, 17 | 27, 20 | 20 | 18 | 18 | 20
2018-10-30 | 12:35 | Marshall | Everyone | 19, 21, 22, 25, 24 | 28, 21 | 25 | 20 | 13 | 18
2018-10-31 | 4:10 | McLain | Everyone | 23, 26, 29, 30, 27 | 22, 23, 24 | 30 | 23 | 8 | 15
2018-11-01 | 12:35 | McLain | Everyone | 31, 32, 34, 36 |  | 34 | 23 | 4 | 15
2018-11-03 | TBA | McLain | Everyone | 33, 35 |  | 36 | 23 | 2 | 15
2018-11-04 | TBA | Troy | Everyone | 37 |  | 37 | 23 | 1 | 15
2018-11-05 | 4:10 | Troy | Everyone | 38 |  | 38 | 23 | 0 | 15
|  | Total Tasks: | 38